## RISK_REGISTER
AEROSPACE PROJECT RISK REGISTER — PMBOK 7 COMPLIANT
Project: AMX-200 Fuselage Coating Program ¦ Leonardo S.p.A. — Divisione Aerostrutture ¦ Status Date: July 2026
ID | Risk Description | Category | Probability (1–5) | Impact (1–5) | Risk Score (P×I) | Priority | Response Strategy | Response Action | Risk Owner | Status | Residual Risk Score | Notes
R-001 | Delay in paint material supply due to single-source supplier | Supply Chain | 4 | 4 | 16 | 🔴 HIGH | Mitigate | Qualify secondary supplier by Week 4; maintain 3-week safety stock | Supply Chain Mgr | Open | 6 | AS9100 clause 8.4 supplier qualification required
R-002 | Non-conformity (NCR) during QA inspection causing rework | Quality | 3 | 5 | 15 | 🔴 HIGH | Mitigate | Weekly QA checkpoints; update control plan; root cause analysis template ready | QA Engineer | Open | 6 | NCR rate target <2% per batch
R-003 | Equipment downtime (spray booths) impacting schedule | Operations | 3 | 4 | 12 | 🟡 MEDIUM | Mitigate | Preventive maintenance schedule monthly; backup booth identified at Nola facility | Maintenance Mgr | Open | 5 | MTTR target <8h
R-004 | Skilled technician unavailability (illness/turnover) | Resource | 2 | 4 | 8 | 🟡 MEDIUM | Accept | Cross-train minimum 2 technicians per process; skills matrix updated quarterly | Production Supervisor | Open | 3 | Critical skill: Sealant application Sez. B
R-005 | Specification change request from customer mid-program | Scope | 2 | 5 | 10 | 🟡 MEDIUM | Transfer | Change control process via CCB; contract clause for scope variation cost recovery | Project Manager | Open | 4 | Requires formal ECR per AS9100 Rev D
R-006 | Environmental regulation update affecting coating chemicals | Compliance | 2 | 3 | 6 | 🟢 LOW | Mitigate | Monitor REACH/RoHS updates quarterly; alternative materials pre-qualified | HSE Manager | Open | 2 | REACH compliance review due Q3 2026
R-007 | Budget overrun due to rising raw material costs | Cost | 3 | 3 | 9 | 🟡 MEDIUM | Mitigate | Monthly cost tracking vs EVM baseline; escalation clause in supplier contracts | Project Manager | Open | 4 | CPI threshold: alert if CPI < 0.90
R-008 | Key subcontractor fails to meet delivery milestone | Supply Chain | 2 | 4 | 8 | 🟡 MEDIUM | Transfer | Liquidated damages clause in subcontract; weekly milestone tracking | Procurement | Open | 3
R-009 | Incorrect surface preparation causing adhesion failure | Quality | 2 | 5 | 10 | 🟡 MEDIUM | Mitigate | Mandatory first-article inspection; surface prep checklist per MIL-SPEC | QA Engineer | Closed | 4 | Closed after additional training — June 2026
R-010 | Weather/humidity exceeding painting process limits | Operations | 3 | 2 | 6 | 🟢 LOW | Accept | Environmental monitoring inside controlled booths; halt procedure if RH>85% | Production Supervisor | Open | 2 | Acceptable residual risk per risk appetite
SUMMARY |  |  | 10 | 2 | 6 | 2 | 9 | 1 | 10 | 16
RISK SCORE = Probability × Impact ¦ 🔴 HIGH ≥ 15 ¦ 🟡 MEDIUM 8–14 ¦ 🟢 LOW < 8 ¦ Residual Risk = Score × 0.4 (after response) ¦ 🔵 Blue = Input ⚫ Black = Formula 🟢 Green = Cross-sheet link

## P×I MATRIX
PROBABILITY × IMPACT MATRIX — Risk Scoring Reference
Each cell shows Risk Score = P × I ¦ Use this matrix to validate your risk scoring in RISK_REGISTER
IMPACT →
PROB ↓ | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
5 Almost Certain | 5 | 10 | 15 | 20 | 25
4 Likely | 4 | 8 | 12 | 16 | 20
3 Possible | 3 | 6 | 9 | 12 | 15
2 Unlikely | 2 | 4 | 6 | 8 | 10
1 Rare | 1 | 2 | 3 | 4 | 5
🔴 HIGH (≥15): Immediate action required — escalate to PM ¦ 🟡 MEDIUM (8–14): Response plan mandatory ¦ 🟢 LOW (<8): Monitor and accept

## RESPONSE_GUIDE
RISK RESPONSE STRATEGIES — PMBOK 7 Reference Guide
Strategy | Definition | Aerospace Example
🔴 AVOID | Eliminate the threat by changing the project plan. Remove the cause or protect the project objective from its impact. | Change coating specification to eliminate use of restricted chemical (REACH compliance risk avoided entirely).
🟡 MITIGATE | Reduce the probability and/or impact of a risk event to an acceptable threshold. | Qualify secondary paint supplier to reduce supply delay probability from 4→2.
🔵 TRANSFER | Shift the negative impact of a risk to a third party (insurance, subcontract, warranty clause). | Include liquidated damages clause in subcontract for milestone delay risk.
🟢 ACCEPT (Active) | Acknowledge the risk and prepare a contingency plan to execute if it occurs. | Accept humidity risk with defined halt procedure if RH>85%. Contingency: reschedule to next dry window.
⚪ ACCEPT (Passive) | Acknowledge the risk with no proactive action. Used for low-priority risks where response cost > impact. | Accept minor schedule float consumption (<1 day) from individual technician absence.
🟣 ESCALATE | Risk is outside project team authority. Escalate to program manager, sponsor, or PMO for decision. | Customer-requested specification change mid-program escalated to CCB (Change Control Board).

## HOW_TO_USE
HOW TO USE THIS RISK REGISTER
Built for aerospace PM — PMBOK 7 aligned ¦ Part of PM Portfolio by Michele Bellarte ¦ github.com/michelebellarte
Step | Action | Detail
1 | Update project header | In RISK_REGISTER row 2, update the project name, company, and status date to match your real project.
2 | Add your risks (blue cells only) | Fill in columns: Risk Description, Category, Probability (1-5), Impact (1-5), Response Strategy, Action, Owner, Status. Risk Score and Priority are calculated automatically.
3 | Use the P×I Matrix sheet | Consult the P×I MATRIX sheet to calibrate your scoring. Use it in team workshops to score risks consistently.
4 | Choose response strategy | Refer to RESPONSE_GUIDE sheet for PMBOK definitions. Choose: Avoid / Mitigate / Transfer / Accept / Escalate.
5 | Interpret Risk Score colors | 🔴 RED (≥15): escalate immediately ¦ 🟡 AMBER (8-14): response plan required ¦ 🟢 GREEN (<8): monitor only.
6 | Track residual risk | Column L shows residual risk after response (Score × 0.4). This represents remaining exposure after your mitigation is applied.
7 | Update status weekly | Change Status column (K) from 'Open' to 'Closed' when risk is resolved. Add closure notes in column M.